## import
level | name | structure | markmap | Show WBS | Yes | markmap | wbsNo | level | name | structure
1 | WBS for Process Improvement Project | 1 WBS for Process Improvement Project | # 1 WBS for Process Improvement Project |  |  | # 1 WBS for Process Improvement Project | 1 | 1 | WBS for Process Improvement Project | 1 WBS for Process Improvement Project
2 | Phase 1: Research and Recommendations | 1.1 Phase 1: Research and Recommendations | ## 1.1 Phase 1: Research and Recommendations |  |  | ## 1.1 Phase 1: Research and Recommendations | 1.1 | 2 | Phase 1: Research and Recommendations | 1.1 Phase 1: Research and Recommendations
3 | Phase 1 Charter | 1.1.1 Phase 1 Charter | ### 1.1.1 Phase 1 Charter |  |  | ### 1.1.1 Phase 1 Charter | 1.1.1 | 3 | Phase 1 Charter | 1.1.1 Phase 1 Charter
3 | Project Management Plans for Phase 1 | 1.1.2 Project Management Plans for Phase 1 | ### 1.1.2 Project Management Plans for Phase 1 |  |  | ### 1.1.2 Project Management Plans for Phase 1 | 1.1.2 | 3 | Project Management Plans for Phase 1 | 1.1.2 Project Management Plans for Phase 1
3 | Research | 1.1.3 Research | ### 1.1.3 Research |  |  | ### 1.1.3 Research | 1.1.3 | 3 | Research | 1.1.3 Research
4 | Documentation of the "State of the Art" | 1.1.3.1 Documentation of the "State of the Art" | #### 1.1.3.1 Documentation of the "State of the Art" |  |  | #### 1.1.3.1 Documentation of the "State of the Art" | 1.1.3.1 | 4 | Documentation of the "State of the Art" | 1.1.3.1 Documentation of the "State of the Art"
5 | Document Search | 1.1.3.1.1 Document Search | ##### 1.1.3.1.1 Document Search |  |  | ##### 1.1.3.1.1 Document Search | 1.1.3.1.1 | 5 | Document Search | 1.1.3.1.1 Document Search
5 | Consultation with Experts | 1.1.3.1.2 Consultation with Experts | ##### 1.1.3.1.2 Consultation with Experts |  |  | ##### 1.1.3.1.2 Consultation with Experts | 1.1.3.1.2 | 5 | Consultation with Experts | 1.1.3.1.2 Consultation with Experts
5 | Benchmarking | 1.1.3.1.3 Benchmarking | ##### 1.1.3.1.3 Benchmarking |  |  | ##### 1.1.3.1.3 Benchmarking | 1.1.3.1.3 | 5 | Benchmarking | 1.1.3.1.3 Benchmarking
5 | Product and Software Review | 1.1.3.1.4 Product and Software Review | ##### 1.1.3.1.4 Product and Software Review |  |  | ##### 1.1.3.1.4 Product and Software Review | 1.1.3.1.4 | 5 | Product and Software Review | 1.1.3.1.4 Product and Software Review
4 | Documentation of the Current State in the Subject Organization | 1.1.3.2 Documentation of the Current State in the Subject Organization | #### 1.1.3.2 Documentation of the Current State in the Subject Organization |  |  | #### 1.1.3.2 Documentation of the Current State in the Subject Organization | 1.1.3.2 | 4 | Documentation of the Current State in the Subject Organization | 1.1.3.2 Documentation of the Current State in the Subject Organization
5 | Interviews | 1.1.3.2.1 Interviews | ##### 1.1.3.2.1 Interviews |  |  | ##### 1.1.3.2.1 Interviews | 1.1.3.2.1 | 5 | Interviews | 1.1.3.2.1 Interviews
5 | Surveys | 1.1.3.2.2 Surveys | ##### 1.1.3.2.2 Surveys |  |  | ##### 1.1.3.2.2 Surveys | 1.1.3.2.2 | 5 | Surveys | 1.1.3.2.2 Surveys
5 | Statistical Analysis | 1.1.3.2.3 Statistical Analysis | ##### 1.1.3.2.3 Statistical Analysis |  |  | ##### 1.1.3.2.3 Statistical Analysis | 1.1.3.2.3 | 5 | Statistical Analysis | 1.1.3.2.3 Statistical Analysis
5 | Flow Charts of Current Processes | 1.1.3.2.4 Flow Charts of Current Processes | ##### 1.1.3.2.4 Flow Charts of Current Processes |  |  | ##### 1.1.3.2.4 Flow Charts of Current Processes | 1.1.3.2.4 | 5 | Flow Charts of Current Processes | 1.1.3.2.4 Flow Charts of Current Processes
3 | Identification of Improvement Needs | 1.1.4 Identification of Improvement Needs | ### 1.1.4 Identification of Improvement Needs |  |  | ### 1.1.4 Identification of Improvement Needs | 1.1.4 | 3 | Identification of Improvement Needs | 1.1.4 Identification of Improvement Needs
4 | Determination of Desired State (Vision Statement) | 1.1.4.1 Determination of Desired State (Vision Statement) | #### 1.1.4.1 Determination of Desired State (Vision Statement) |  |  | #### 1.1.4.1 Determination of Desired State (Vision Statement) | 1.1.4.1 | 4 | Determination of Desired State (Vision Statement) | 1.1.4.1 Determination of Desired State (Vision Statement)
4 | Gap Analysis | 1.1.4.2 Gap Analysis | #### 1.1.4.2 Gap Analysis |  |  | #### 1.1.4.2 Gap Analysis | 1.1.4.2 | 4 | Gap Analysis | 1.1.4.2 Gap Analysis
4 | Most Likely Solutions | 1.1.4.3 Most Likely Solutions | #### 1.1.4.3 Most Likely Solutions |  |  | #### 1.1.4.3 Most Likely Solutions | 1.1.4.3 | 4 | Most Likely Solutions | 1.1.4.3 Most Likely Solutions
5 | Brainstorming | 1.1.4.3.1 Brainstorming | ##### 1.1.4.3.1 Brainstorming |  |  | ##### 1.1.4.3.1 Brainstorming | 1.1.4.3.1 | 5 | Brainstorming | 1.1.4.3.1 Brainstorming
5 | Statistical Analysis | 1.1.4.3.2 Statistical Analysis | ##### 1.1.4.3.2 Statistical Analysis |  |  | ##### 1.1.4.3.2 Statistical Analysis | 1.1.4.3.2 | 5 | Statistical Analysis | 1.1.4.3.2 Statistical Analysis
5 | Flow Charts of Desired Processes | 1.1.4.3.3 Flow Charts of Desired Processes | ##### 1.1.4.3.3 Flow Charts of Desired Processes |  |  | ##### 1.1.4.3.3 Flow Charts of Desired Processes | 1.1.4.3.3 | 5 | Flow Charts of Desired Processes | 1.1.4.3.3 Flow Charts of Desired Processes
3 | Recommendations | 1.1.5 Recommendations | ### 1.1.5 Recommendations |  |  | ### 1.1.5 Recommendations | 1.1.5 | 3 | Recommendations | 1.1.5 Recommendations
4 | Recommendation 1 | 1.1.5.1 Recommendation 1 | #### 1.1.5.1 Recommendation 1 |  |  | #### 1.1.5.1 Recommendation 1 | 1.1.5.1 | 4 | Recommendation 1 | 1.1.5.1 Recommendation 1
5 | Draft Charter | 1.1.5.1.1 Draft Charter | ##### 1.1.5.1.1 Draft Charter |  |  | ##### 1.1.5.1.1 Draft Charter | 1.1.5.1.1 | 5 | Draft Charter | 1.1.5.1.1 Draft Charter
5 | Estimated Cost | 1.1.5.1.2 Estimated Cost | ##### 1.1.5.1.2 Estimated Cost |  |  | ##### 1.1.5.1.2 Estimated Cost | 1.1.5.1.2 | 5 | Estimated Cost | 1.1.5.1.2 Estimated Cost
4 | Recommendation 2 | 1.1.5.2 Recommendation 2 | #### 1.1.5.2 Recommendation 2 |  |  | #### 1.1.5.2 Recommendation 2 | 1.1.5.2 | 4 | Recommendation 2 | 1.1.5.2 Recommendation 2
5 | Draft Charter | 1.1.5.2.1 Draft Charter | ##### 1.1.5.2.1 Draft Charter |  |  | ##### 1.1.5.2.1 Draft Charter | 1.1.5.2.1 | 5 | Draft Charter | 1.1.5.2.1 Draft Charter
5 | Estimated Cost | 1.1.5.2.2 Estimated Cost | ##### 1.1.5.2.2 Estimated Cost |  |  | ##### 1.1.5.2.2 Estimated Cost | 1.1.5.2.2 | 5 | Estimated Cost | 1.1.5.2.2 Estimated Cost
4 | Recommendation 3 | 1.1.5.3 Recommendation 3 | #### 1.1.5.3 Recommendation 3 |  |  | #### 1.1.5.3 Recommendation 3 | 1.1.5.3 | 4 | Recommendation 3 | 1.1.5.3 Recommendation 3
5 | Draft Charter | 1.1.5.3.1 Draft Charter | ##### 1.1.5.3.1 Draft Charter |  |  | ##### 1.1.5.3.1 Draft Charter | 1.1.5.3.1 | 5 | Draft Charter | 1.1.5.3.1 Draft Charter
5 | Estimated Cost | 1.1.5.3.2 Estimated Cost | ##### 1.1.5.3.2 Estimated Cost |  |  | ##### 1.1.5.3.2 Estimated Cost | 1.1.5.3.2 | 5 | Estimated Cost | 1.1.5.3.2 Estimated Cost
2 | Phase 2: Implementation of Approved Recommendation (This portion of the WBS is repeated for each approved recommendation) | 1.2 Phase 2: Implementation of Approved Recommendation (This portion of the WBS is repeated for each approved recommendation) | ## 1.2 Phase 2: Implementation of Approved Recommendation (This portion of the WBS is repeated for each approved recommendation) |  |  | ## 1.2 Phase 2: Implementation of Approved Recommendation (This portion of the WBS is repeated for each approved recommendation) | 1.2 | 2 | Phase 2: Implementation of Approved Recommendation (This portion of the WBS is repeated for each approved recommendation) | 1.2 Phase 2: Implementation of Approved Recommendation (This portion of the WBS is repeated for each approved recommendation)
3 | Recommendation x Charter (approved and amended version of the draft from 1.1.5) | 1.2.1 Recommendation x Charter (approved and amended version of the draft from 1.1.5) | ### 1.2.1 Recommendation x Charter (approved and amended version of the draft from 1.1.5) |  |  | ### 1.2.1 Recommendation x Charter (approved and amended version of the draft from 1.1.5) | 1.2.1 | 3 | Recommendation x Charter (approved and amended version of the draft from 1.1.5) | 1.2.1 Recommendation x Charter (approved and amended version of the draft from 1.1.5)
3 | Project Management Plans for Phase 2 (seven plans | 1.2.2 Project Management Plans for Phase 2 (seven plans | ### 1.2.2 Project Management Plans for Phase 2 (seven plans |  |  | ### 1.2.2 Project Management Plans for Phase 2 (seven plans | 1.2.2 | 3 | Project Management Plans for Phase 2 (seven plans | 1.2.2 Project Management Plans for Phase 2 (seven plans
3 | Process Documentation | 1.2.3 Process Documentation | ### 1.2.3 Process Documentation |  |  | ### 1.2.3 Process Documentation | 1.2.3 | 3 | Process Documentation | 1.2.3 Process Documentation
4 | Draft process (policy | 1.2.3.1 Draft process (policy | #### 1.2.3.1 Draft process (policy |  |  | #### 1.2.3.1 Draft process (policy | 1.2.3.1 | 4 | Draft process (policy | 1.2.3.1 Draft process (policy
4 | Review | 1.2.3.2 Review | #### 1.2.3.2 Review |  |  | #### 1.2.3.2 Review | 1.2.3.2 | 4 | Review | 1.2.3.2 Review
4 | Revision (1.2.3.2 and 1.2.3.3 are iterative—repeat until there is consensus) | 1.2.3.3 Revision (1.2.3.2 and 1.2.3.3 are iterative—repeat until there is consensus) | #### 1.2.3.3 Revision (1.2.3.2 and 1.2.3.3 are iterative—repeat until there is consensus) |  |  | #### 1.2.3.3 Revision (1.2.3.2 and 1.2.3.3 are iterative—repeat until there is consensus) | 1.2.3.3 | 4 | Revision (1.2.3.2 and 1.2.3.3 are iterative—repeat until there is consensus) | 1.2.3.3 Revision (1.2.3.2 and 1.2.3.3 are iterative—repeat until there is consensus)
4 | Publication | 1.2.3.4 Publication | #### 1.2.3.4 Publication |  |  | #### 1.2.3.4 Publication | 1.2.3.4 | 4 | Publication | 1.2.3.4 Publication
5 | Hardcopy | 1.2.3.4.1 Hardcopy | ##### 1.2.3.4.1 Hardcopy |  |  | ##### 1.2.3.4.1 Hardcopy | 1.2.3.4.1 | 5 | Hardcopy | 1.2.3.4.1 Hardcopy
5 | Internet or Intranet | 1.2.3.4.2 Internet or Intranet | ##### 1.2.3.4.2 Internet or Intranet |  |  | ##### 1.2.3.4.2 Internet or Intranet | 1.2.3.4.2 | 5 | Internet or Intranet | 1.2.3.4.2 Internet or Intranet
5 | Other | 1.2.3.4.3 Other | ##### 1.2.3.4.3 Other |  |  | ##### 1.2.3.4.3 Other | 1.2.3.4.3 | 5 | Other | 1.2.3.4.3 Other
3 | Tools (software | 1.2.4 Tools (software | ### 1.2.4 Tools (software |  |  | ### 1.2.4 Tools (software | 1.2.4 | 3 | Tools (software | 1.2.4 Tools (software
4 | Design | 1.2.4.1 Design | #### 1.2.4.1 Design |  |  | #### 1.2.4.1 Design | 1.2.4.1 | 4 | Design | 1.2.4.1 Design
4 | Build | 1.2.4.2 Build | #### 1.2.4.2 Build |  |  | #### 1.2.4.2 Build | 1.2.4.2 | 4 | Build | 1.2.4.2 Build
4 | Test | 1.2.4.3 Test | #### 1.2.4.3 Test |  |  | #### 1.2.4.3 Test | 1.2.4.3 | 4 | Test | 1.2.4.3 Test
4 | Revision (1.2.4.3 and 1.2.4.4 are iterative—repeat until the product meets its goals) | 1.2.4.4 Revision (1.2.4.3 and 1.2.4.4 are iterative—repeat until the product meets its goals) | #### 1.2.4.4 Revision (1.2.4.3 and 1.2.4.4 are iterative—repeat until the product meets its goals) |  |  | #### 1.2.4.4 Revision (1.2.4.3 and 1.2.4.4 are iterative—repeat until the product meets its goals) | 1.2.4.4 | 4 | Revision (1.2.4.3 and 1.2.4.4 are iterative—repeat until the product meets its goals) | 1.2.4.4 Revision (1.2.4.3 and 1.2.4.4 are iterative—repeat until the product meets its goals)
4 | Implementation | 1.2.4.5 Implementation | #### 1.2.4.5 Implementation |  |  | #### 1.2.4.5 Implementation | 1.2.4.5 | 4 | Implementation | 1.2.4.5 Implementation
3 | Training | 1.2.5 Training | ### 1.2.5 Training |  |  | ### 1.2.5 Training | 1.2.5 | 3 | Training | 1.2.5 Training
4 | Instructors | 1.2.5.1 Instructors | #### 1.2.5.1 Instructors |  |  | #### 1.2.5.1 Instructors | 1.2.5.1 | 4 | Instructors | 1.2.5.1 Instructors
5 | Hiring | 1.2.5.1.1 Hiring | ##### 1.2.5.1.1 Hiring |  |  | ##### 1.2.5.1.1 Hiring | 1.2.5.1.1 | 5 | Hiring | 1.2.5.1.1 Hiring
5 | Training (“Train the Trainers”) | 1.2.5.1.2 Training (“Train the Trainers”) | ##### 1.2.5.1.2 Training (“Train the Trainers”) |  |  | ##### 1.2.5.1.2 Training (“Train the Trainers”) | 1.2.5.1.2 | 5 | Training (“Train the Trainers”) | 1.2.5.1.2 Training (“Train the Trainers”)
4 | Development | 1.2.5.2 Development | #### 1.2.5.2 Development |  |  | #### 1.2.5.2 Development | 1.2.5.2 | 4 | Development | 1.2.5.2 Development
5 | Draft Training Materials | 1.2.5.2.1 Draft Training Materials | ##### 1.2.5.2.1 Draft Training Materials |  |  | ##### 1.2.5.2.1 Draft Training Materials | 1.2.5.2.1 | 5 | Draft Training Materials | 1.2.5.2.1 Draft Training Materials
5 | Review and Pilot | 1.2.5.2.2 Review and Pilot | ##### 1.2.5.2.2 Review and Pilot |  |  | ##### 1.2.5.2.2 Review and Pilot | 1.2.5.2.2 | 5 | Review and Pilot | 1.2.5.2.2 Review and Pilot
5 | Revision (1.2.5.2.2 and 1.2.5.2.3 are iterative—repeat until the class meets its goals) | 1.2.5.2.3 Revision (1.2.5.2.2 and 1.2.5.2.3 are iterative—repeat until the class meets its goals) | ##### 1.2.5.2.3 Revision (1.2.5.2.2 and 1.2.5.2.3 are iterative—repeat until the class meets its goals) |  |  | ##### 1.2.5.2.3 Revision (1.2.5.2.2 and 1.2.5.2.3 are iterative—repeat until the class meets its goals) | 1.2.5.2.3 | 5 | Revision (1.2.5.2.2 and 1.2.5.2.3 are iterative—repeat until the class meets its goals) | 1.2.5.2.3 Revision (1.2.5.2.2 and 1.2.5.2.3 are iterative—repeat until the class meets its goals)
4 | Delivery | 1.2.5.3 Delivery | #### 1.2.5.3 Delivery |  |  | #### 1.2.5.3 Delivery | 1.2.5.3 | 4 | Delivery | 1.2.5.3 Delivery
2 | Phase 3: Evaluation | 1.3 Phase 3: Evaluation | ## 1.3 Phase 3: Evaluation |  |  | ## 1.3 Phase 3: Evaluation | 1.3 | 2 | Phase 3: Evaluation | 1.3 Phase 3: Evaluation
3 | Project Management Plans for Phase 3 (seven plans | 1.3.1 Project Management Plans for Phase 3 (seven plans | ### 1.3.1 Project Management Plans for Phase 3 (seven plans |  |  | ### 1.3.1 Project Management Plans for Phase 3 (seven plans | 1.3.1 | 3 | Project Management Plans for Phase 3 (seven plans | 1.3.1 Project Management Plans for Phase 3 (seven plans
3 | Documentation of the New State in the Subject Organization | 1.3.2 Documentation of the New State in the Subject Organization | ### 1.3.2 Documentation of the New State in the Subject Organization |  |  | ### 1.3.2 Documentation of the New State in the Subject Organization | 1.3.2 | 3 | Documentation of the New State in the Subject Organization | 1.3.2 Documentation of the New State in the Subject Organization
4 | Interviews | 1.3.2.1 Interviews | #### 1.3.2.1 Interviews |  |  | #### 1.3.2.1 Interviews | 1.3.2.1 | 4 | Interviews | 1.3.2.1 Interviews
4 | Surveys | 1.3.2.2 Surveys | #### 1.3.2.2 Surveys |  |  | #### 1.3.2.2 Surveys | 1.3.2.2 | 4 | Surveys | 1.3.2.2 Surveys
4 | Statistical Analysis | 1.3.2.3 Statistical Analysis | #### 1.3.2.3 Statistical Analysis |  |  | #### 1.3.2.3 Statistical Analysis | 1.3.2.3 | 4 | Statistical Analysis | 1.3.2.3 Statistical Analysis
4 | Flow Charts of New Processes | 1.3.2.4 Flow Charts of New Processes | #### 1.3.2.4 Flow Charts of New Processes |  |  | #### 1.3.2.4 Flow Charts of New Processes | 1.3.2.4 | 4 | Flow Charts of New Processes | 1.3.2.4 Flow Charts of New Processes
3 | Identification of Deficiencies | 1.3.3 Identification of Deficiencies | ### 1.3.3 Identification of Deficiencies |  |  | ### 1.3.3 Identification of Deficiencies | 1.3.3 | 3 | Identification of Deficiencies | 1.3.3 Identification of Deficiencies
4 | Flow Charts of Desired Processes (from 1.4.3.3) | 1.3.3.1 Flow Charts of Desired Processes (from 1.4.3.3) | #### 1.3.3.1 Flow Charts of Desired Processes (from 1.4.3.3) |  |  | #### 1.3.3.1 Flow Charts of Desired Processes (from 1.4.3.3) | 1.3.3.1 | 4 | Flow Charts of Desired Processes (from 1.4.3.3) | 1.3.3.1 Flow Charts of Desired Processes (from 1.4.3.3)
4 | Gap Analysis | 1.3.3.2 Gap Analysis | #### 1.3.3.2 Gap Analysis |  |  | #### 1.3.3.2 Gap Analysis | 1.3.3.2 | 4 | Gap Analysis | 1.3.3.2 Gap Analysis
3 | Recommendations for New Projects | 1.3.4 Recommendations for New Projects | ### 1.3.4 Recommendations for New Projects |  |  | ### 1.3.4 Recommendations for New Projects | 1.3.4 | 3 | Recommendations for New Projects | 1.3.4 Recommendations for New Projects
4 | Recommendation 1 | 1.3.4.1 Recommendation 1 | #### 1.3.4.1 Recommendation 1 |  |  | #### 1.3.4.1 Recommendation 1 | 1.3.4.1 | 4 | Recommendation 1 | 1.3.4.1 Recommendation 1
5 | Draft Charter | 1.3.4.1.1 Draft Charter | ##### 1.3.4.1.1 Draft Charter |  |  | ##### 1.3.4.1.1 Draft Charter | 1.3.4.1.1 | 5 | Draft Charter | 1.3.4.1.1 Draft Charter
5 | Estimated Cost | 1.3.4.1.2 Estimated Cost | ##### 1.3.4.1.2 Estimated Cost |  |  | ##### 1.3.4.1.2 Estimated Cost | 1.3.4.1.2 | 5 | Estimated Cost | 1.3.4.1.2 Estimated Cost
4 | Recommendation 2 | 1.3.4.2 Recommendation 2 | #### 1.3.4.2 Recommendation 2 |  |  | #### 1.3.4.2 Recommendation 2 | 1.3.4.2 | 4 | Recommendation 2 | 1.3.4.2 Recommendation 2
5 | Draft Charter | 1.3.4.2.1 Draft Charter | ##### 1.3.4.2.1 Draft Charter |  |  | ##### 1.3.4.2.1 Draft Charter | 1.3.4.2.1 | 5 | Draft Charter | 1.3.4.2.1 Draft Charter
5 | Estimated Cost | 1.3.4.2.2 Estimated Cost | ##### 1.3.4.2.2 Estimated Cost |  |  | ##### 1.3.4.2.2 Estimated Cost | 1.3.4.2.2 | 5 | Estimated Cost | 1.3.4.2.2 Estimated Cost
4 | Recommendation n | 1.3.4.3 Recommendation n | #### 1.3.4.3 Recommendation n |  |  | #### 1.3.4.3 Recommendation n | 1.3.4.3 | 4 | Recommendation n | 1.3.4.3 Recommendation n
5 | Draft Charter | 1.3.4.3.1 Draft Charter | ##### 1.3.4.3.1 Draft Charter |  |  | ##### 1.3.4.3.1 Draft Charter | 1.3.4.3.1 | 5 | Draft Charter | 1.3.4.3.1 Draft Charter
5 | Estimated Cost | 1.3.4.3.2 Estimated Cost | ##### 1.3.4.3.2 Estimated Cost |  |  | ##### 1.3.4.3.2 Estimated Cost | 1.3.4.3.2 | 5 | Estimated Cost | 1.3.4.3.2 Estimated Cost
Atlas will import your structure from columns A and B, ignoring rows where either is blank.